# Minutes

Bicycle Board Education Committee

Meeting date: 12 February, 2009

Meeting location: 245 Allison Street (Becker’s house)

Meeting objective: Plan Education Grant Implementation

Participants: Jim Rye, Don Spencer, Paul Becker (scribe), Chip Wamsley, Frank Gmeindl, Nick Hein

Action Items:

| Due date | Responsibility | Action Item |
| --- | --- | --- |
| 4/9/09 | Jim Rye | Coordinate possible grad students and Hugh Kierig to establish connections with appropriate WVU people to work with us on this project. |
| 4/9/09 | Chip Wamsley | Contact Graham Pease re web 2.0 |
| May | Chip Wamsley | Contact Bonnie Anderson re: student help with marketing; also Paula Bone and Strat Douglas |
| 4/9/09 | Paul Becker | Meet with Jim Rye and develop a preliminary metrics plan. |
| 4/9/09 | Don Dickerson | Contact Dan Lohman about making a video Public Service Announcement |
| 4/9/09 | Chip Wamsley | Continue to work with B&E for marketing students |
| 4/9/09 | Jim Rye | Investigate with Mridul Gautum re: writing prelim proposal for major bike education grant |
| 4/9/09 | Paul Becker Nick Hein | Make contact with 4-H re: spring ride and cooperation on youth educational events |
| 3/9/09 (?) | Gmeindl | Bring Federal Highways pilot proposal idea to whole bike board; or spend the allocated $35,000 on Share the Road Signs |

Discussion/Conclusions:

- Discussed various contacts in WVU, including employee wellness program for sponsoring Traffic Safety 101.   New player is Kimberly Zapf.   Mikorski can’t give date yet.

- Discussed how rigorous measurement of outcomes needed to be.   Outcomes need to be driven by stated goals in proposal.

- We have missed the window to get WVU communications, journalism, marketing faculty and students involved in the spring semester.   The curriculum for MBA’s is fairly rigorous and we need to get in the door in end of May.   Contacts include Graham Pease, Bonnie Anderson (best hookup for us) Paula Bone and Strat Douglas.

- Research corp offers opportunity to support a major 5 yr grant proposal with approx $50,000.   Preproposal needed and Jim will explore.

- Frank Gmeindl discussed upcoming Statewide Bicycle Symposium.   There’s lots of enthusiasm and resources, but not a clear plan or desired outcome.  He’s trying to help with that.   Not clear that wellness is involved in the planning.   Dates are April 17-18.

- Frank has agreement from M’town police to offer Traffic Skills 101 to police officers (not necessarily bike officers)   He will tailor the class to increase/improve officers’ knowledge and respect for bicyclists rights and responsibilities.   Expects to be challenging but fruitful.   4-8 officers will attend the first session.

- Alternatives to failed lane signage proposal were discussed.  Idea is to apply to Federal Highway Administration to do a pilot.  Frank suggests not fighting the battle of Shared Lane Markings but going for traditional Share the Road signage.  These signs are also generally educational about bicycle rights.  WVDOH would install the Share the Road signs at their expense on roads that they maintain.

Agenda for Next Meeting:

The next Education Committee meeting will be the second Thursday of April 9, tentatively at Becker house 245 Allison Street.   An agenda wasn’t defined at this meeting.